## Background and Instructions
South Carolina 2025 BEAD Grant Program Capital Investment Schedule
Background
BEAD NOFO Section IV.D.2.c
Applicants must submit a capital investment schedule evidencing complete build-out and the initiation of service within four years of the date on which the entity receives the subgrant.
Conditional Limited Programmatic Waiver and Clarification of Professional Engineer (PE) Certification
The Capital Investment Schedule does not need to be certified by a professional engineer.
Instructions
The Applicant should complete the "Detailed Costs" tab first and then the "Capital Investment Schedule" tab. Upload the completed worksheet into the ShareFile file [BEAD Main Application and Technical Capability Attachments subfolder]. While the build out schedule must be completed within four (4) years, applicants can develop the project faster and do not need to include costs for all four (4) years if the project will be completed sooner than four (4) years (e.g., the project will be fully complete in two (2) years). Yellow cells are for Applicant inputs, while red cells contain automatically calculated values and do not require any entry from Applicants.
Tab Instructions
Tab | Description
Detailed Costs | Applicants must enter individual cost items into the “Detailed Costs” tab. The Detailed Costs tab must be completed first so the totals may populate the "Capital Investment Schedule" tab category totals. For each proposed cost item, the applicant must fill out the following information fields:
Cost Item: A simple description of the cost item. (e.g., Direct Salaries – Directional Drilling, Material - Handhole, Contracting Services - OSP Design Engineering).
Category: This is a drop-down field for each of the program cost categories. The Applicant should select the field that is appropriate for the proposed cost item. Descriptions of the costs categories can be found in the "Description of Project Cost Categories" table below.
Unit Type: The unit of measurement for each cost item quantity (e.g., feet, each, hours)
Unit Quantity: The Applicant’s estimated quantity of each cost item that will be required to complete the project.
Unit Cost: The estimated cost per unit for each cost item.
Cost Details and Justification: The Applicant should provide sufficient narrative supporting their estimated unit quantities and cost. The Applicant can use this field to provide additional details such as proposed construction methodologies and materials specifications.
Detailed Costs - Reference | There is no action for Applicants on the reference tab. Cost Items listed are from South Carolina's ARPA 3.0. The list is illustrative of possible cost items to include and should not be considered an exhaustive reference for Applicants as they build their detailed costs table.
Capital Investment Schedule | For each applicable quarter, the applicant must provide the funds expected to be expensed each quarter. The capital investment schedule expenditures must match the total expenditures for each cost category. Cost items associated with the "Contingencies" cost category will not be entered into the capital investment schedule as they represent a contingency and not costs the Applicant anticipates incurring.
Description of Project Cost Categories
Please review the Main Application Guidelines for more detail regarding eligible and ineligible expenses
Category | Description
Planning/Project Management/Grant Management | Items pertaining to the management of the Applicant’s internal staff or third-party contractors. Items could include but are not limited to: internal project management, grant management hours, and administrative staff hours associated with planning, project management, and grant management.
Design Engineering | Items pertaining to the design of the Applicant’s proposed project. Items could include but are not limited to: OSP engineering contractor costs, in-house field surveys and CAD designs, the preparation of permit application documentation, or civil engineering costs for structural attachments.
Permitting | All costs and fees associated with permitting. Items could include but are not limited to: fees associated with right-of-way permits, environmental permits, railroad crossing permits, and pole application permits.
Right of Way/Easement Acquisition | Reasonable expenses for right of way or private easements to facilitate the network deployment. Items could include but are not limited to: reasonable expenses for right of way or private easements, make-ready fees for aerial attachments, purchasing of dark fiber/existing conduit space, and the purchasing of colocation space for network equipment.
Network Deployment | All costs associated with the deployment of the proposed network, excluding components exclusive to subscriber activations (i.e., network drop construction, customer premises equipment). Items could include but are not limited to: directional drilling labor, conduit material, fiber optic cable material, construction equipment, etc. Please note, an ineligible expense is the purchase of equipment that is depreciable and has a useful life after project completion, unless it is part of the facilities used to deliver the broadband service (e.g., fiber, conduit, electronics, etc.)
Network Equipment | All costs associated with the purchase of network electronics and active equipment. Items could include but are not limited to: network switches, network routers, and Cabinets/ Optical Line Terminals. The Applicant should indicate the proposed make and model of the equipment being purchased.
Subscriber Activations | Costs associated with the connection of subscribers. Items could include but are not limited to: subscriber drop construction, subscriber drop materials, and customer premises equipment. Please note, installation costs are not eligible if the consumer is charged an installation fee.
Miscellaneous | Any costs not captured by the other categories. The Applicant must provide sufficient narrative describing each item listed under this category.
Contingencies | Any contingency costs the applicant anticipates along with a narrative description of why the costs are anticipated.
Cost Notes
A. If actual construction costs exceed budget, the Applicant will be required to complete the project with no additional BEAD funds.
B. SC Initial Proposal Vol. II - The SCBBO will deploy Broadband infrastructure projects on a Fixed amount subaward basis with demonstrated evidence of eligible costs incurred, which will allow the State to withhold funds if the subgrantee fails to complete the project. Clawback provisions will be included in all grant agreements between the State and any subgrantee. Other clawback provisions may include drawing on the letter of credit required by all grantees. If a subgrantee fails to perform and fails to return the full forfeited amount required, the state retains the right to pursue any legal action or remedy and to the extent applicable, any costs and attorneys’ fees expended or incurred in pursuing such legal remedies.
Note to SCBBO: Once the workbook is finalized, we will lock tabs/cells where needed to prevent Applicants from adjusting content/formulas and hide the Data Validation tab.

## Detailed Costs
South Carolina 2025 BEAD Grant Program Capital Investment Schedule
Please enter all costs for deployment to BSLs in the project area.
Cost Item | Category | Unit Type | Unit Quantity | Unit Cost | Total Cost (Auto-Calculated) | Cost Details and Justification
Engineering Design | Design Engineering | Hour | 50 | 500 | 25000 | Staking & GIS
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Insert new rows above

## Detailed Costs - Reference
South Carolina 2025 BEAD Grant Program Capital Investment Schedule
Below are sample Cost Items from South Carolina's ARPA 3.0. The list is illustrative of possible cost items to include and should not be considered an exhaustive reference for Applicants as they build their detailed costs table.
Cost Item | Category
Direct Salaries - Engineering | Design Engineering
Direct Salaries - Construction | Network Deployment
Direct Salaries - Project Management | Planning/Project Management/Grant Management
Direct Salaries - Grant Management | Planning/Project Management/Grant Management
Direct Overhead - Engineering | Design Engineering
Direct Overhead - Construction | Network Deployment
Direct Overhead - Project Management | Planning/Project Management/Grant Management
Direct Overhead - Grant Management | Planning/Project Management/Grant Management
Contracting Services - Engineering | Design Engineering
Contracting Services - Construction | Network Deployment
Internal Vehicle Overhead | Network Deployment
Permitting | Permitting
Railroad Crossing | Permitting
Right of Way/Easement Acquistion | Right of Way/Easement Acquisition
Fiber | Network Deployment
Cabinets / OLTs (Optical Line Terminal) | Network Equipment
ONTs (Optical Network Terminal) | Network Equipment
Conduit | Network Deployment
Handhole | Network Deployment
Pedestals | Network Deployment
Pole Attachment Hardware | Network Deployment
Other Materials & Supplies | Miscellaneous
Freight | Miscellaneous

## Capital Investment Schedule
South Carolina BEAD Grant Program Capital Investment Schedule
Instructions: For each applicable quarter, the Applicant must provide the funds expected to be expensed each quarter. The "Sum of Detailed Costs" column is auto-calculated from the "Detailed Costs" tab. The "Sum of Quarterly Costs" is auto-calculated as Applicants input quarterly cost data.
| If "Sum of Detailed Costs" and "Sum of Quarterly Cost" do not match, please review the "Detailed Costs" tab to ensure all costs listed have been included in the "Quarterly Cost" allocations. |  | Quarterly Cost for all BSLs in Project Area Please allocate the total cost for each category into the quarter(s) it will be spent. The sum of the quarterly costs should match each category's total cost.
The "Sum of Quarterly Costs" cells will turn green when they equal the "Sum of Detailed Costs".
Category | Sum of Detailed Costs (Auto-calculated) | Sum of Quarterly Costs (Auto-calculated) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16
Planning/Project Management/Grant Management | 0 | 0
Design Engineering | 25000 | 0
Permitting | 0 | 0
Infrastructure Acquisition | 0 | 0
Network Deployment | 0 | 0
Network Equipment | 0 | 0
Subscriber Activations | 0 | 0
Miscellaneous | 0 | 0
Contingencies | 0 | 0 | Q1: Quarterly allocations for "Contingencies" are not required.
Total | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## DataVal
Project Cost Categories
Planning/Project Management/Grant Management
Design Engineering
Permitting
Right of Way/Easement Acquisition
Network Deployment
Network Equipment
Subscriber Activations
Miscellaneous
Contingencies